## Slide 1: “Post-Disaster Needs Assessment and Recovery in Vietnam”
S3.5 Overview of Recovery and Reconstruction Issues

## Slide 2: Session Objectives
To provide an overview of key considerations for post-disaster recovery and reconstruction
  Managing and coordinating disaster reconstruction
  Addressing recovery and reconstruction needs
  Needs versus damages and losses
  Planning and budgeting for reconstruction
  Implementing reconstruction

## Slide 3: Managing and coordinating disaster reconstruction
Many actors in recovery, requires coordination: government (depts / sectors / political officials), private sector, development partners
Is a special reconstruction agency required, or is there an existing institution to address disaster management?
  Reconstruction after ‘smaller’ disasters
Avoiding delays between disaster response, and disaster reconstruction
  Balance between reconstruction planning process and urgent implementation needs
Planning
Speed

## Slide 4: Addressing Recovery and Reconstruction Needs
Recovery is about re-establishing basic public services, as well as capital investments for reconstruction.
As with normal investments, remember recurrent spending for Operations & Maintenance
Disaster Relief
Disaster Reconstruction

## Slide 5: Needs may be different to the damage/loss assessment
Higher needs (costs)
  ‘Build back better’ (quality, mitigation)
  High-speed procurement, contracting, logistics, administration etc. may incur higher costs
  Price inflation (resource scarcity)
Lower needs (costs)
  Insurance coverage (formal or informal risk transfer)
  Reduced public service demand (migration)

## Slide 6: Planning and Budgeting for Reconstruction
Reconstruction needs based on sector damage/loss assessments; normal investment based on previous performance.
  Priorities are identified differently
Annual sector budgets vs. reconstruction process
  Budget cycles rarely match
  On-budget, off-budget

## Slide 7: Planning and Budgeting for Reconstruction: managing budgets
Planning
Budgeting
Implementation
Accounting & Reporting
Internal/ External Reporting
Results M&E
DaLNA
Budget preparation & approval
Sector & consolidated planning
Procurement & disbursement
Accounting & Reporting
Internal / External Reporting
Results M&E
Typical, regular public (expenditure) financial management process
Post-disaster public financial management process
Note: Off-budget funds are more likely in post-disaster PFM

## Slide 8: Implementing Reconstruction
We need reconstruction arrangements that are fast, yet apply key public financial management principles.
  What is the ‘trigger’ to adopt reconstruction arrangements instead of normal arrangements?
  Quickly translating needs assessment to a plan & budget
  Decision to use regular procurement vs. special procurement mechanisms

## Slide 9: Implementing Reconstruction
Monitoring systems and oversight necessary to ensure best use of reconstruction funds and resources
  Realistic & frequent monitoring schedule
  Monitor & supervise contractors to ensure quality
  Evaluate individual reconstruction activities, and overall Sector reconstruction
Reconstruction must be credible and show accountability to encourage further funding
  Use of on-budget / off-budget funds

## Slide 10: In summary…
Reconstruction should be
  Responsive to identified needs and priorities
  Timely, beginning and continuing at a fast pace
  Cost-effective (within the constraints of urgency and scope)
  Accountable and credible (funds used for intended purpose)
Process relies on good information and communication
Additional information at “Managing Post-Disaster Reconstruction Finance: International Experience in Public Financial Management” (WB, 2008).

## Slide 11: Group Exercise
In the main sector groups
Based on the project implementation plans (Step 6), please identify for monitoring and evaluation:
  Who will conduct
  How will it be conducted
  When will it be conducted